## pre registry week
| 12 weeks prior | 10 weeks prior | 8 weeks prior | 6 weeks prior | 4 weeks prior | 2 weeks prior | 1 week prior
Build the local campaign team infrastructure and build political will | attend 100k Homes Campaign orientation call, fourth Wednesday of every month | convene local campaign leadership team in person and create these planning committees: Housing Support services Targeted Communities (maps) Donations- material resources Survey week logistics and Volunteers Media PR Marketing Database-Registry-HMIS | send out flyer and wufoo link to get 100 volunteers | create local facebook page | communicate with volunteers about registry week and sign up more if needed | send out notification to press of what you will be doing
| fill out campaign leadership team diagram - start with what you've got and recruit more! | enroll in 100k Homes Campaign (enrollment wufoo, data wufoo, terms of use) | set a housing placement goal for your community
| outreach to hospital psych ED, medical ED, medical inpatient, psych inpatient, or Social Work director to assess whether or not homeless frequent users are an issue for this hospital and invite to the campaign leadership team if yes. | set up meetings with elected officials to begin securing their support | recruit additional members for the campaign leadership team
begin work on HIPAA release to be able to do VI surveys inside the hospitals
Clarify the Demand |  | decide whether you want to send 2 people to learn thru a registry week or if you want to host 2 co-facilitators; seek local United Way or foundation support to cover this cost. | identify institutions for surveying (shelters, jails, hospitals, detox) | select survey time - should be 2 hours prior to when most people wake up on the streets | identify centrally located training/convening site for registry week & a place for data entry with good wifi | send outreach teams out to camps to spread the word that the surveys will be happening; hospital staff can also give a head's up to frequent patients | assemble team leader folders
|  | ask hospitals to assemble their by-name frequent user list for future comparison to VI survey results | identify geographic area of focus, hidden encampments, etc. | estimate how many surveys will be completed | identify names of organizations to be included on the release permission form, including hospitals | choose survey incentives and procure from local vendors | print copies of release and survey
|  |  | assign someone to be "registry list keeper" for the local campaign team" | identify outreach team leaders, if applicable. | line up police support if necessary | local champion complete story-of-self worksheet and discuss with campaign team
Line-up the Supply | complete community inventory all existing resources that could provide housing subsidy and pay for supportive services |  | housing and services committees refine discussions about allocation of resources including section 8 thru Housing Authority, VA, 202 housing, supportive housing providers, FQHCs, human service departments, and respite care or recuperative care beds | secure commitments for housing authority Section 8 preference, VASH, S+C, McKinney Vento Bonus, CDBG funds, 202 & 811 housing | identify additional innovations from other communities you want to adapt and get started on it! | re-convene campaign leadership team to firm up housing placement commitment
|  |  | assign someone to be the "inventory keeper" for the local campaign team | connect with Urban Land Institute or local real estate groups to enlist landlords
Coordinated access system to match people to housing & services | Identify all housing providers and service delivery organizations |  | compile list of required documents for each housing type | housing authorities and providers train housing placement or outreach teams on completing applications
within housing committee, identify a liaison for these sub-groups: VA, Seniors, Youth, and Frequent Users
Retain in Housing |  | Kick-off meeting with providers and tenants, assessment of what it takes to house people. | Identify criteria / requirements of each housing program, or respite program. advocate for inclusion of most vulnerable | Develop individualized “coming home” plan / tool.
|  | Identify community based primary care providers who can be enlisted post-housing to provide care | Identify capacity, interest and resources for housing for the first wave | Identify possible sources of income for people. Look into SOAR teams to expedite SSI applications
Firm up pre-application / pre-housing process checklist
Note on D2: bkanis: see if local organizing for america will partner

## during registry week
| Monday | Tuesday | Wednesday | Thursday | Friday
Build the local campaign team infrastructure and build political will |  | make sure VIPs are coming to the de-brief | identify super-volunteer from among registry week volunteers | pre-brief conference call with campaign leadership team and VIPs | community de-brief and press conference
commitment cards with volunteers
Clarify the Demand
Line-up the Supply |  |  | meetings with supply sources as possible | create landlord call-in line | meet with supply people after community de-brief *H2H: incl hospitals and FQHCs re: PCP, respite, match list to freq users
ask to local landlords as part of press conference
Coordinated access system to match people to housing & services
Retain in Housing | Tweak out questions for first wave of prioritized people |  | Identify volunteers who could take a role in promoting housing retention, i.e. mentoring
Emphasis in orientation / messaging about retention

## post registry week
| 1st week post-registry | 2nd week post-registry | 3rd week post-registry | 4th week post-registry | 6th week post-registry | 8th week post-registry
Build the local campaign team infrastructure and build political will | re-convene campaign leadership team to match registry week findings to inventory | 1st cohort of individuals move into housing
| super volunteer begins mailing list based on results of commitment cards | teams of volunteers assemble welcome packages
| convene outreach teams to match against their lists | capture move-ins w/ flip for campaign social media
| coordinate media coverage of move-ins | get oped published in local paper
| if doing H2H, match frequent user list to VI survey results | local press story about move-in of most vulnerable
Clarify Demand | establish way for on-going input into the registry |  |  | re-run the hospital frequent user list and re-match against updated registry. repeat on a monthly basis going forward
Line up Supply | Match up registry results to existing inventory and identify any gaps
Coordinated access system to match people to housing & services | conduct housing and services assessment with people | conduct housing and services assessment with people | conduct housing and services assessment with people | conduct housing and services assessment with people | conduct housing and services assessment with people | conduct housing and services assessment with people
| educate tenants about expectations and housing options | educate tenants about expectations and housing options | educate tenants about expectations and housing options | educate tenants about expectations and housing options | educate tenants about expectations and housing options | educate tenants about expectations and housing options
| work with tenants to get benefits, income, housing, health insurance & PCP | work with tenants to get benefits, income, housing, health insurance & PCP | work with tenants to get benefits, income, housing, health insurance & PCP | work with tenants to get benefits, income, housing, health insurance & PCP | work with tenants to get benefits, income, housing, health insurance & PCP | work with tenants to get benefits, income, housing, health insurance & PCP
| assess tenant preferences and needs using CTI template | assess tenant preferences and needs using CTI template | assess tenant preferences and needs using CTI template | assess tenant preferences and needs using CTI template | assess tenant preferences and needs using CTI template | assess tenant preferences and needs using CTI template
Retain in Housing | Program introduction to landlords -- "sell" what's in it for you | 1-2-1 meetings with landlords to address expectations / concerns, building relationships, communications |  | broaden "circle of care"
Income/ID/relationship establishment (w/in first two weeks of working w/ person)

## facilitation milestones
| Monday | Tuesday | Wednesday | Thursday | Friday
Co-facilitators alongside community champion | start training off with story of self | start day off w/ 2 stories of self | start day off w/ 2 stories of self | start day off with story of us | de-brief volunteers first (Charlotte model)
| 3 hour training that incorporates public narrative and how-to (Denver model) | facilitate team return and de-briefs | facilitate team return and de-briefs | facilitate team return and de-briefs | community de-briefing
| breakout groups to train proofreaders, team muse, picture downloaders, and team leaders | train data entry team | re-allocate teams as needed | complete data entry by 1 pm | hand out commitment cards at de-brief
|  | tally up team results (% who agreed, # photographs) | tally up team results (% who agreed, # photographs) | data analysis and briefing prep
| update facebook page | update facebook page | update facebook page | update facebook page | update facebook page
| capture flip stories of volunteer experiences | capture flip stories of volunteer experiences | capture flip stories of volunteer experiences | make flip mini-movie for de-brief and fb page | capture flip stories of volunteer experiences
|  | make sure VIPs are coming to the de-brief | identify & recruit the das uber volunteer | hand out commitment cards to volunteers | celebration (Denver model)
give commitment cards to the das uber